## ISO27001 Risk Register
Risk ID | Vulnerability / Risk Title | Risk Description | Asset Affected | Threat Source | Likelihood | Impact | Risk Score | Risk Level | Risk Owner | Existing Controls | Mitigation Plan | Residual Risk | Status | Reference
RSK-001 | Anonymous FTP Enabled | FTP service permits unauthenticated anonymous login access to files and directories. | FTP Server | External attacker | High (3) | High (3) | 9 | Critical | Security Team | VM Isolation | Disable anonymous FTP access and enforce authentication | Low | Open | Nmap Scan
RSK-002 | Telnet Service Enabled | Telnet transmits credentials and communication in plaintext across the network. | Telnet Service | Network attacker | High (3) | High (3) | 9 | Critical | System Administrator | Internal Lab Network | Replace Telnet with SSH and disable Telnet service | Low | Open | Nmap Enumeration
RSK-003 | SMB Signing Disabled | SMB signing disabled may allow SMB relay and man-in-the-middle attacks. | SMB Service | Internal attacker | High (3) | Medium (2) | 6 | High | IT Security Team | Host-only Adapter | Enable SMB signing on all systems | Low | Open | SMB Enumeration
RSK-004 | Outdated Apache HTTP Server | Apache 2.2.8 server contains publicly known vulnerabilities and outdated components. | Apache Web Server | Remote attacker | High (3) | High (3) | 9 | Critical | Web Administrator | Basic Firewall | Upgrade Apache to latest supported version | Medium | Open | Nikto Findings
RSK-005 | HTTP TRACE Method Enabled | HTTP TRACE method may expose session information and support Cross-Site Tracing attacks. | Web Server | Web attacker | Medium (2) | Medium (2) | 4 | Medium | Web Security Team | Default Apache Config | Disable TRACE method on web server | Low | Open | Nikto Scan
RSK-006 | Directory Listing Enabled | Web server allows directory indexing and browsing of internal files. | Apache Web Server | External attacker | Medium (2) | Medium (2) | 4 | Medium | Web Administrator | Limited Access Controls | Disable directory indexing and apply access restrictions | Low | Open | Nikto Findings
RSK-007 | Exposed phpMyAdmin Interface | Publicly accessible phpMyAdmin interface detected on web application. | phpMyAdmin | Remote attacker | Medium (2) | High (3) | 6 | High | Database Administrator | Internal Lab Usage | Restrict phpMyAdmin access and enforce authentication | Medium | Open | Nikto Enumeration
RSK-008 | Weak SSL/TLS Cipher Support | Weak encryption ciphers may allow downgrade or interception attacks. | HTTPS Service | Man-in-the-middle attacker | Medium (2) | Medium (2) | 4 | Medium | Security Administrator | Default SSL Configuration | Disable weak ciphers and enforce strong TLS settings | Low | Open | SSL Enumeration
RSK-009 | Exposed VNC Service | VNC remote desktop service exposed to the network without sufficient restrictions. | VNC Service | Remote attacker | Medium (2) | High (3) | 6 | High | System Administrator | Internal Access Controls | Restrict VNC access and enable authentication | Medium | Open | Nmap Service Detection
RSK-010 | Outdated Apache Tomcat Service | Outdated Tomcat server may permit remote exploitation and application compromise. | Tomcat Server | Remote attacker | High (3) | High (3) | 9 | Critical | Server Administrator | Internal Testing Environment | Upgrade or remove vulnerable Tomcat service | Medium | Open | Nmap Service Scan
RSK-011 | SMBv1 Protocol Enabled | SMBv1 protocol contains multiple known remote code execution vulnerabilities. | SMB Service | Internal attacker | Medium (2) | High (3) | 6 | High | IT Security Team | Firewall Segmentation | Disable SMBv1 and migrate to SMBv3 | Low | Open | SMB Enumeration
RSK-012 | Default Credentials on Services | Default usernames and passwords increase unauthorized access risk. | Web/Remote Services | External attacker | High (3) | High (3) | 9 | Critical | Security Administrator | Limited Network Exposure | Change all default credentials immediately | Low | Open | Manual Review
RSK-013 | Exposed MySQL Service | MySQL database service publicly accessible over the network. | MySQL Database | Remote attacker | Medium (2) | High (3) | 6 | High | Database Administrator | Internal Network Segmentation | Restrict remote database access | Medium | Open | Nmap Enumeration
RSK-014 | Outdated Samba Service | Samba service version contains known security vulnerabilities. | Samba Service | Internal attacker | High (3) | Medium (2) | 6 | High | System Administrator | Internal Host-only Network | Update Samba to latest secure version | Medium | Open | Nmap Version Detection
RSK-015 | PostgreSQL Service Exposure | PostgreSQL database service exposed to unauthorized network access. | PostgreSQL Database | Remote attacker | Medium (2) | High (3) | 6 | High | Database Team | Local VM Isolation | Restrict PostgreSQL external access | Medium | Open | Service Enumeration
RSK-016 | Legacy Services Exposure | Multiple outdated and unnecessary services increase attack surface significantly. | Entire VM Environment | External/Internal attacker | High (3) | High (3) | 9 | Critical | Infrastructure Team | Virtual Lab Isolation | Disable unused legacy services | Medium | Open | Nmap Full Scan
RSK-017 | Weak Web Server Security Headers | Missing HTTP security headers may permit browser-based attacks. | Apache Web Server | Web attacker | Medium (2) | Medium (2) | 4 | Medium | Web Security Team | Basic Apache Configuration | Configure security headers properly | Low | Open | Nikto Scan
RSK-018 | Open IRC Service Exposure | UnrealIRCd service exposed and potentially vulnerable to exploitation. | IRC Service | Remote attacker | Medium (2) | High (3) | 6 | High | Network Administrator | Host-only Network | Disable or secure IRC service | Medium | Open | Nmap Enumeration
RSK-019 | NFS Service Exposure | NFS shares may expose sensitive files to unauthorized systems. | NFS Service | Internal attacker | Medium (2) | Medium (2) | 4 | Medium | System Administrator | Local Lab Network | Restrict NFS access permissions | Low | Open | Nmap Scan
RSK-020 | Weak Patch Management | Multiple outdated services indicate poor patch management practices. | Entire Target Environment | Remote attacker | High (3) | High (3) | 9 | Critical | Infrastructure Team | Periodic Updates | Implement regular patch management procedures | Medium | Open | Overall Assessment